## ASME REVIEW 2014
No | Title :ASME Review Planner and Schedule
Program Schedule
| Description of Task | Person |  | 2014-01-01
resposible | time axis 2014-01-01 to 2014-12-31
 | time axis 2014-01-01 to 2014-12-31
A | Client Name: |  | 2014-01-15: Kawan Engineering Sdn Bhd; 2014-01-22: Kawan Engineering Sdn Bhd; 2014-02-10: Kawan Engineering Sdn Bhd; 2014-03-10: Synchong Hoe Eng Sdn Bhd; 2014-03-26: Synchong Hoe Eng Sdn Bhd; 2014-04-01: Jutasama Sdn Bhd; 2014-04-10: Jutasama Sdn Bhd; 2014-05-07: Tenaga Tiub; 2014-05-21: Tenaga Tiub
1 | Provide Quotation
Receive Official PO
2 | Prepare and submit ndt document
RT Procedure No:
UT Procedure No:
MT Procedure No:
PT Procedure No:
3 | Get appoiment letter of Ndt level III
Reply acceptance of level II appoinment
4 | List of Ndt Personnel
Name:Level III
Name:Level III
Name:Level II
Name:Level II
Name:Level II
Name:Level II
Name:Level II
5 | Check Personnel File
comply to ASME requirement
6 | List of Equipment involve in ASME review
Check equipment record and calibration
comply to ASME requirement
7 | Demostration
| RT demo |  | 2014-01-15: Demo
MT/PT demo
UT demo
RT demo report
MT/PT demo report
UT demo report
8 | Pre review ASME |  | 2014-01-22: Kawan Eng Sdn BhdPre-review Kawan; 2014-03-10: Pre-review 10/3/2014; 2014-04-01: Jutasama 1/4/14; 2014-05-07: Tenaga Tiub 7-8/5/14
9 | Actual ASME review |  | 2014-02-10: Actual Review; 2014-03-26: 2013-03-26; 2014-04-10: Jutasama 10/4/14; 2014-05-21: Tenaga Tiub 21-22/5/14; 2014-09-17: Chip Ngai Eng
Name of Team Leader
Remarks
Demo
Pre-review
Actual